## Consolidated
S. No. | Tester | Area | Observation/Description/ Steps to reproduce | Category (H) | Status (I) | Severity | Resource | Remarks | Type | Status | Area | Resource | Remarks Mac testing
1 | Kazim | Video | In filter Online user option should be available | Suggestion | Acknowledged |  | Arsalan | Tweak | TBD | Acknowledged | News Ticker | Omair
2 | Kazim | Video | By default only online users should be visible in the list | Suggestion | Acknowledged |  | Arsalan | Randomly missing online user in different browsers from list | Roadmap | Resolved | File Sync | Hamza | ok
3 | Kazim | Video | Recent and Missed option should be combine | Suggestion | Acknowledged |  | Arsalan | TBD | Suggestion | Tested | Calendar | Arsalan | ok
4 | Kazim | Video | When ever user hover an icon or text, field should be highlighted | Suggestion | Acknowledged |  | Arsalan | TBD | Other | Ignore | Access Management | Fahad | ok
5 | Kazim | File Sync | On hover member name should display | Suggestion | Acknowledged |  | Arsalan | Tweak | Bug | Unresolved | Authorization | Danish | ok
6 | Kazim | File Sync | Date format to be same in all feature | Suggestion | Acknowledged |  | Arsalan | Remaining in Insight Deposit Base | Performance | Discussion | Settings | Ovais
7 | Kazim | File Sync | After renaming the file or perform any activity container begins to load, This should not happen | Suggestion | Acknowledged |  | Arsalan | Tweak |  | Open | Deposit Sheet | Rafhan
8 | Kazim | File Sync | Member word replace with Shared User | Suggestion | Acknowledged |  | Arsalan | Tweak |  | Test Again | Rate Sheet | Faizan
9 | Kazim | File Sync | Today activity file should be displayed in different color | Suggestion | Acknowledged |  | Arsalan | Tweak |  | Re-Open | Notes
10 | Yaqoob | Audit Trial | In user login history most of the record are not correct repeating records in logged in time. | Bug | Re-Open |  | Arsalan | Email sent to Arsalan. |  |  | Audit Trial
11 | Yaqoob | Audit Trial | In user login history decrease records size like 80% screen | Suggestion | Open |  | Rafhan |  |  |  | Notification |  | ok
12 | Yaqoob | Audit Trial | In user login logs records exceeding "to Time" range | Bug | Acknowledged | [5 empty] | Address Book |  | ok
13 | Yaqoob | Audit Trial | In user login detail page not responsive with different screen | Suggestion | Open |  | Rafhan |  |  |  | Daily Digest |  | ok
14 |  | File Sync | When create a new independent folder during moving a file folder created under a previous folder. Display on front screen just for a while | Bug | Acknowledged |  | Arsalan |  |  |  | Media |  | ok
15 | Yaqoob | Audit Trial | Date picker need to be better | Suggestion | Open |  | Rafhan |  |  |  | Greeting Screen
16 |  | Video | Multiple click option not working when trying to create group call | Bug | Acknowledged |  | Arsalan |  |  |  | Markets
17 |  | Video | New Call notification donot appear when user on other or minimize the browser. | Suggestion | Acknowledged |  | Arsalan |  |  |  | SideBar
18 |  | File Sync | Sharing a file - open file sharing screen, selected no user and press Done. Cancel and Done button disabled | Bug | Acknowledged |  | Arsalan |  |  |  | Talk App |  | ok
19 | Yaqoob | Audit Trial | Paste not working on right click | Bug | Open |  | Rafhan |  |  |  | Search |  | ok
20 |  | File Sync | Star functionality is not working properly. Consult with Fahad on this. | Bug | Acknowledged |  | Arsalan |  |  |  | General |  | ok
21 | Ovais | Axis API | Conversation token is not returning in initiate video call request. | Bug | Resolved |  | Hamza |  |  |  | User Profile |  | ok
22 |  | File Sync | Small screen need to be changed as given in Axismain. | Suggestion | Acknowledged |  | Arsalan | Design not properly implemented |  |  | Feeds
23 |  | Video | Only single video screen will open as updated on Axismain. | Suggestion | Acknowledged |  | Arsalan |  |  |  | Email |  | issue in safari
24 | Ovais | Axis API | Call should be intimated on the web, if initiated from the postman. (For testing purpose) | Other | Resolved |  | Hamza |  |  |  | Internal News |  | ok
25 | Ovais | Axis API | The end point leave-video-call producing error. | Bug | Resolved |  | Hamza |  |  |  | Talk |  | ok
26 | Yaqoob | Video | Unable to click multile check box in video panel for group call | Bug | Acknowledged |  | Arsalan |  |  |  | Login Screen
27 | Yaqoob | Calendar | By default all events are creating on All day | Bug | Acknowledged |  | Danish |  |  |  | Insights |  | ok
28 | Kazim | Calendar | Calendar event not reflecting in real time | Bug | Acknowledged |  | Hamza | Functional Issue |  |  | User Status |  | `
29 | Yaqoob | File Sync | View only right user should not be able to have edit, download and share option both in NC and Axis | Bug | Acknowledged |  | Arsalan |  |  |  | Minisite |  | ok
30 | Yaqoob | File Sync | When Amna reshared a file ,File was not shared with Shumaila | Bug | Acknowledged |  | Arsalan |  |  |  | Video
31 | Yaqoob | File Sync | Farhat shared a file , I edit the file, Then farhat edit the file my changes disappeared. | Bug | Acknowledged |  | Arsalan | Arsalan : Functionality change, file can not be share with file owner |  |  | Project
32 | Yaqoob | File Sync | When share a file with a user, user file sync screen layout gets disturbed | Bug | Acknowledged |  | Arsalan
33 | Kazim | Calendar | when change filter icon alignment get disturbed | Bug | Acknowledged |  | Hamza | Tweak
34 | Kazim | Calendar | Popout notification for reminder of upcoming event in calendar should appear | Suggestion | Open |  | Rafhan | Roadmap
35 | Yaqoob | File Sync | When upload a folder with files in it. All files appearing on front screen except All in Windows | Suggestion | Acknowledged |  | Arsalan
36 | Kazim | Video | Share screen not working | Bug | Open |  | Danish | Functional Issue
37 | Kazim | File Sync | Recent order issue when change filter | Bug | Acknowledged |  | Danish | details please i have already sent you the share date, sorting can be done your site
38 | Kazim | File Sync | When open whiteboard NC begins to download zip files | Bug | Re-Open |  | Danish | it will only download the files when the file you are trying to open doest not exists.
39 | Yaqoob | File Sync | Shared file disappear from recent tab after open in collabora | Bug | Acknowledged |  | Danish | not from my side i think, if it is breif please.
40 | Yaqoob | File Sync | Download all files started when open any file in nc | Bug | Acknowledged |  | Danish | it will only download the files when the file you are trying to open doest not exists. |  |  |  |  | ok
41 | Yaqoob | File Sync | When ever click a file, File should not open NC page | Bug | Acknowledged |  | Danish | if the file is there on nexcloud it will open, first it will open nc page then the file will open
42 | Yaqoob | File Sync | Collabora not working pls check | Bug | Acknowledged |  | Danish | Functional Issue
43 | Kazim | Calendar | Create event will be replaced with Calendar icon. when user click on icon calendar open user will click date to create event | Suggestion | [8 empty] | ok
44 | Yaqoob | Video | All participant names not displaying in whitboard 4:03 | Bug | Open |  | Danish | [5 empty] | ok
45 | Yaqoob | Video | Changes not saved in whiteboard displaying blank screen 3:51 / Check with NC behaviour first | Bug | Open |  | Danish | [5 empty] | ok
46 | Kazim | Calendar | Past event color should be changed | Roadmap |  |  |  | TBD
47 | Kazim | Calendar | Event duplicate or repeat the same event functionaly should be develop | Roadmap |  |  |  | Roadmap |  |  |  |  | ok
48 | Kazim | Calendar | Video call link should be availble in calendar | Roadmap |  |  |  | Roadmap |  |  |  |  | ok
49 | Waqas | Calendar | While creating event hour selection option should not be dependent on AM, PM | Roadmap |  |  |  | TBD
50 | Waqas | Calendar | While creating event video link option should be available | Roadmap |  |  |  | TBD |  |  |  |  | ok
51 | Waqas | Calendar | When add attendee email to attendee not generating | Suggestion | Open | Critical | Rafhan | Design required.
52 | Yaqoob | Calendar | Event Title field should be mandatory | Roadmap | Open | Critical
53 |  | Calendar | When adding attendees suggestion box is so stretched | Suggestion | Acknowledged |  | Rafhan | [5 empty] | not ok
54 | Yaqoob | Calendar | By default all events are creating on All day | Bug
55 | Yaqoob | Calendar | Calendar Invitation confirmation option is missing | Roadmap | Open | Critical | [6 empty] | ok
56 | Yaqoob | Calendar | Unable to click on event to view details | Suggestion | Open | Critical | Danish | Pending at Danish end.
57 | Yaqoob | Calendar | Calendar Invititation confirmation or Reject option should be available in NC Calendar | Suggestion | Open |  | Danish
58 | Shoaib | Calendar | Whenever user select day, month and year it should reflect the day time slots, month days and calender months respectively
59 | Shoaib | Calendar | It should be possbile to edit or delete any event.
60 | Shoaib | Calendar | Event; Location: Drop drop menu should be available as soon as user start to type locations.
61 | Shoaib | Calendar | How to add calender notes?
62 | Shoaib | Calendar | How to set attendees rights (e.g modify or delete, view)
63 | Iqra | Calendar | Attendee received notification when the event was created, but they did not receive email invite. | Suggestion | Open |  |  | Email not working currently from NC.
64 | Iqra | Calendar | unable to view details on the calendar by clicking on it. | Suggestion | Open | Critical | Danish | Duplicate of Issue 56.
65 | Farhat | Calendar | Attendees not rcvd multiple notifiaction ( created 3 diff events,Attendee rcv only 1 Notification) | Bug | Acknowledged | Critical | Arsalan
66 | Farhat | Calendar | Give format bar (Bold,Italic,Link etc)in description | Roadmap | Open | Critical
67 | Yaqoob | File Sync | Row separation Lines are not properly implemented. Disappear on folders | Bug | Acknowledged |  | Fahad
68 | Waqas | Calendar | Event is not showing when change calendar view from week to month | Bug | Ignore
69 | Yaqoob | Calendar | Event not reflecting on real time also modal not closing after creating the event | Bug
71 | Asif | Calendar | When I update an event on Calendar, not showing me any notification that it is updated.
72 | Yaqoob | Video | already on call and try to initiate another call and cancel my desicion than side bar and leave call buttons will hide on current call | Bug | Acknowledged |  | Fahad | [5 empty] | ok
73 | Shoaib | Email | Just after the configration email, the email widget section shouldn't be just blank. | Bug | Acknowledged |  | Arsalan | Functional Issue
74 | Yaqoob | Email | when email is open, on performing mark as Junk / Mark as read / Delete, toast pop up should appear. | Suggestion | Acknowledged |  | Arsalan | [5 empty] | ok
75 | Kazim | Email | Discard option should be replaced with Bin Icon | Suggestion | Acknowledged |  | Fahad | Tweak |  |  |  |  | ok
76 | Kazim | Email | In Compose email after adding ID backspace space option not working to remove the ID | Suggestion | Acknowledged |  | Fahad | Tweak |  |  |  |  | ok
77 | Kazim | Email | In Compose email, Save and exit option should be in Button format | Suggestion | Acknowledged |  | Fahad | Tweak |  |  |  |  | ok
78 | Kazim | Email | In compose email, Email word to be replaced with Compose Email | Suggestion | Acknowledged |  | Fahad | Tweak
79 | Kazim | Email | Need to change color for unread emails | Suggestion | Acknowledged |  | Fahad | Tweak |  |  |  |  | ok
80 | Kazim | Email | On hover date. email time should be displayed | Suggestion | Acknowledged |  | Fahad | Tweak
81 | Kazim | Email | On hover sender name all participant in emails should be displayed on hover | Suggestion | Acknowledged |  | Fahad | Rafhan bhai working on it. |  |  |  |  | ok
82 | Kazim | Email | Need to give check box to perform repeated action in single step | Suggestion | Acknowledged |  | Fahad | Screen not updating on real time
83 | Kazim | Email | Highlight row when hover and select email | Suggestion | Acknowledged |  | Fahad | Tweak
84 | Asif | Email | When user enter the next line, Space showing between the line | Other | Acknowledged |  | Fahad | Tweak
85 | Kazim | Email | ID should be editable even after pressing tab | Suggestion | Acknowledged |  | Fahad | Tweak
86 | Kazim | Email | Recipients word to be replaced with TO , Correct Cc and Bcc | Suggestion | Acknowledged |  | Fahad | Tweak
87 | Kazim | Email | Unable to move Email ID from one field to different field like TO to cc, CC to BCC | Suggestion | Acknowledged |  | Fahad | Tweak |  |  |  |  | ok
88 | Kazim | Email | When send an email to my own ID Profile picture showing dummy image this should be removed | Suggestion | Acknowledged |  | Fahad | [5 empty] | ok
89 | Kazim | Email | Hand Cursor on clickabe item like email dropdown list, attachment in email, | Suggestion | Acknowledged |  | Fahad | Just dropdown left
90 |  | Email | Remove borders with attachments | Suggestion | Acknowledged |  | Fahad
91 |  | Email | Star functionality not working properly. | Bug | Acknowledged |  | Fahad | [5 empty] | ok
92 | Yaqoob | Email | Email by default opening in medium screen pls check | Bug | Acknowledged |  | Fahad
93 | Yaqoob | Email | Bcc is missing in tooltip list in dropdown and in hover. It should only be shown when the configured user is a sender. | Suggestion | Acknowledged |  | Fahad | Its not a bug. Its our understanding that bcc is not shown to anyone thats why we not showing bcc
94 | Yaqoob | Email | When delete an email then undo from Trash Tool tip donot work in Inbox | Bug | Acknowledged |  | Fahad
95 | Yaqoob | Email | Mark as not Junk option is missing while mark as junk by using check boxes | Suggestion | Acknowledged |  | Fahad | Just identified and assigned.
96 | Yaqoob | Email | Counter not working properly when delete all messages. For ref, check gmail | Bug | Acknowledged |  | Fahad
97 | Ovais | Email | Mark as unread icon to replace Unread Icon in menu list | Bug | Acknowledged |  | Fahad
98 | Yaqoob | Email | When select all email , undo and Unread icon to be required with tool tip in trash | Suggestion | Acknowledged |  | Fahad
99 | Kazim | Email | When Configure email system donot allow to use Axis other widgets untill all email get synced | Bug | Acknowledged |  | Hamza | Functional Issue
100 | Kazim | Email | When undo trash email, Email appear at the bottom of the Inbox | Bug | Not Reproducible |  | Hamza | Functional Issue
101 | Kazim | Email | In Compose email, setting option should be removed | Suggestion | Acknowledged |  | Hamza | Tweak
102 | Kazim | Email | Alignment issues | Bug | Acknowledged |  | Hamza | Tweak
103 | Kazim | Email | Attachment clip size to be small | Suggestion | Acknowledged |  | Hamza | Tweak
104 | Yaqoob | Email | Recurring: After optimization, perform reply all system giving space between IDs and also repeating IDs | Bug | Acknowledged |  | Hamza
105 | Yaqoob | Email | Need to remove double arrow and setting option when user Replying all the email. | Suggestion | Acknowledged |  | Hamza | Tweak |  |  |  |  | ok
106 | Yaqoob | Email | Displaying x on start of Email ID when email send to user | Bug | Acknowledged |  | Hamza | Functional Issue
107 | Farhat | Email | new email not shown as updated in my gmail inbox need to refresh it | Bug | Not Reproducible |  | Hamza | Functional Issue
108 | Farhat | Email | No notification of new email | Bug | Not Reproducible |  | Hamza | Functional Issue
109 | Yaqoob | Email | When forward an email with attachement, Attachment not displaying | Bug | Acknowledged |  | Hamza | Functional Issue
110 | Kazim | Email | When Forward an email with multiple attachment unable to delete any particular file from attachments | Bug | Acknowledged |  | Hamza | Functional Issue
111 | Ovais | Email | On selection of SECP, Kibor, Conversion Rates, Customer Rates and FX Reval Rates, Email table headings get removed. | Bug | Acknowledged |  | Hamza | Functional Issue |  |  |  |  | ok
112 | Yaqoob | Email | Saved draft not reflecting in Draft screen | Bug | Acknowledged |  | Hamza
113 | Yaqoob | Email | When Re forward an email with attachment, Attachment has been disappeared | Bug | Acknowledged |  | Hamza | [5 empty] | ok
114 | Yaqoob | Email | When Forward an email with multiple attachments , Attachment disappeared | Bug | Acknowledged |  | Hamza
115 | Yaqoob | Video | If user is already on call and someone call him then modal doesnot show who is calling. and when he rejects the call modal is not closing. | Bug | Acknowledged |  | Hamza
116 | Yaqoob | Video | Left Participant also getting whiteboard notification with full control | Bug | Re-Open |  | Hamza | Hamza : file id is not returning in response. |  |  |  |  | ok
117 | Waqas | Email | Replying to all - when replying to all, my email address is not being removed from the mailing list | Bug | Acknowledged |  | Hamza | [5 empty] | ok
118 | Kazim | Email | System should pick email ID without pressing enter | Suggestion | Acknowledged |  | Rafhan | Tweak
119 | Kazim | Email | Back button should be available during composing | Suggestion | Acknowledged |  | Rafhan | Tweak |  |  |  |  | ok
120 | Kazim | Email | Inbox, Sent, Delete etc option should be displayed in label format or give in mini icons | Roadmap | Discussion |  | Rafhan | Roadmap |  |  |  |  | ok
121 | Iqra | Email | While composing a new email, the system should suggest the id's of people with whom I've already communicated. I have to write whole email address | Suggestion | Acknowledged |  | Fahad | [5 empty] | ok
122 | Shoaib | Email | Tool tip for compose the new email should be read as "Compose an email" or "New Message" instead of "New". | Suggestion | Acknowledged |  | Rafhan | Duplicate |  |  |  |  | ok
123 | Yaqoob | Email | Remove borders with attachments | Suggestion | Acknowledged |  | Rafhan | [5 empty] | ok
124 |  | Email | When click on star option, dropdown should be closed. | Suggestion | Ignore |  |  | Star option is now deleted from the list. |  |  |  |  | ok
125 | Yaqoob | Email | Cursor should be left aligned with Subject in To, Cc, Bcc | Suggestion | Open |  | Rafhan
126 | yaqoob | Email | After entering ID when user press space bar cursor should appear beside the ID and then click tab cursor should move to next field |  | Re-Open |  | Rafhan | While writing email, select email from the suggestion list and press tab, system appending email twice. Cursor should be there after pressing tab, enter or spacebar. |  |  |  |  | Axis blur check with rafhan
127 | Kazim | Email | Compose email screen should be separate so that user can see backend screen | Roadmap | Open | Critical
128 | Kazim | Email | Need to implement sorting mechanism in email | Roadmap |  |  |  | Roadmap
129 | Asif | Email | Unable to find editing tools on the main screen of compose email. | Bug | Not Reproducible |  |  | Functional Issue
130 | Asif | Email | No notification of new email | Bug | Not Reproducible |  |  | Functional Issue
131 | Yaqoob | Email | Popup should appear on any activity like incoming or outgoing emails etc | Suggestion | Acknowledged | Critical | Arsalan | Toast message to be displayed on sending of email only.
132 | Yaqoob | Email | Sent not updating | Bug | Acknowledged |  | Fahad | Ok on live working fine
133 | Waqas | Email | Email chain should develop | Roadmap | Open | Critical
134 | Farhat | Email | Old sent item not synced | Bug | Not Reproducible |  |  | User Understanding Issue
135 | Kazim | Video | When click any option user dont intimate that open has been clicked | Suggestion | Resolved |  | Arsalan | Unable to check
136 | Kazim | Video | After leaving the call system keeping blank space at the bottom of the page | Bug | Acknowledged |  | Rafhan
137 | Farhat | Email | reply to email in sent items not shown as updated in gmail account | Other |  |  |  | TBD |  |  |  |  | ok
138 | Kazim | Video | In kazim system on changing resolution of the screen video screen alignment out | Bug | Acknowledged |  | Rafhan | [5 empty] | ok
139 | Kazim | Video | When user is on another call, connected icon to display video icon | Suggestion | Re-Open |  | Arsalan | Displaying all users are connected. |  |  |  |  | ok
140 | Kazim | Video | Video and other panel size should be decreased | Suggestion | Resolved |  | Arsalan | [5 empty] | ok
141 | Iqra | Email | All categories except Inbox, including Sent item and Draft are empty, previous emails are not replicated. | Other |  |  |  | User Understanding Issue
142 | Shoaib | Email | Email folders should be synchronize (i.e. Inbox, Sent, Draft & etc.) | Other |  |  |  | User Understanding Issue
143 | Kazim | Email | Every attachment should open on screen instead of download to single click | Roadmap | Open | Critical
144 | Kazim | Email | Image paste option not working in compose email | Bug | Acknowledged |  | Fahad | [5 empty] | ok
145 | Yaqoob | Email | Next and Previous email option should be available when user has opened an email. | Suggestion | Open | Critical | Arsalan | Designed by Rafhan.
146 | Yaqoob | Email | Required Address not found email in axis email | Suggestion | Acknowledged |  | Hamza | [5 empty] | ok
147 | Yaqoob | Email | IF To, CC ID are wrong and bcc email is right system not sending the email to the correct ID also email failure email did not receive | Bug | Acknowledged | Critical | Fahad
148 | Yaqoob | Email | Please remove setting and double arrow in sign in screen | Suggestion | Ignore
149 | Yaqoob | Email | Loader should not appear on the email that already opened /read | Suggestion | Open | Critical | Fahad
150 | Waqas | Email | My sent emails are shown in " Drafts" | Other | Acknowledged | [7 empty] | ok
151 | Waqas | Email | If I am marking any email with "star", it is not showing on my mailbox | Roadmap | Discussion |  |  | Backward synchronization.
152 | Yaqoob | Email | When delete few records from Email, system donot auto load next email to balance the 25 counter in every dropdown option. | Suggestion | Resolved | Critical | Fahad | It is deleting one by one, too slow process. Pls optimize. |  |  |  |  | ok
153 | Yaqoob | Email | Do not load all types of emails initially, load on demand only. Only inbox emails to be loaded initially. | Suggestion | Acknowledged |  | Fahad
154 | Yaqoob | Email | I have scrolled down to the last email in the list and then changed the page. The vertical scrollbar is at the same position. It should go on the top. | Suggestion | Acknowledged |  | Fahad
155 | Yaqoob | Email | On clicking the refresh button, I should go to the first page of the email. | Suggestion | Acknowledged |  | Fahad
156 | Kazim | Video | Chat option not working | Roadmap |  |  |  | Roadmap
157 | Kazim | Video | When host leave the call, Call should be close to all participant or give an option to assign new host | Roadmap |  |  |  | NC default functionality
158 | Yaqoob | Email | Loader should only be visible on email initial loading of Inbox. For all other loading operations, show text "Loading…" on the email header, same like Gmail does. | Suggestion | Acknowledged |  | Fahad
159 | Yaqoob | Email | After pressing the Send button, the toast message has to be shown with the text "Sending Email".And user will redirect to selected screen | Suggestion | Acknowledged |  | Fahad
160 | Kazim | Video | No notification of upcoming call when user on other tab or using different application | Bug | Not Reproducible |  |  | Functional Issue
161 | Kazim | Video | Check option should be available in video contact list | Suggestion | Acknowledged |  |  | Already Available
162 | Kazim | Video | One user should be active in one call only | Roadmap |  |  |  | Discarded
163 | Kazim | Video | If a user is on another call message should be displayed to caller | Roadmap |  |  |  | TBD
164 | Kazim | Video | Block user option should be available | Suggestion |  |  |  | Discarded
165 | Yaqoob | Email | If the email sent successfully, the toast message has to be shown with the text "Email Sent", and if not successful, then "Error in sending email". | Suggestion | Ignore |  | Fahad
166 | Yaqoob | Email | Right click paste option not working where as ctrl +V is working during compose an email | Bug
167 | Yaqoob | Email | Axis Internal Usage email could not send from Axis Email. | Bug
168 | Shoaib | Email | Add the same email id two or more times then click on the send button, check the inbox of that id, it should be mention only once at TO field.
169 | Kazim | File Sync | File should open on same screen | Roadmap |  |  |  | TBD
170 | Kazim | File Sync | Checkbox in file Sync | Roadmap |  |  |  | Roadmap
171 | Shoaib | Email | Whenever user try to send email without subject or empty body then an alert message should be there as *Send this message without a subject or text in the body?* | [9 empty] | ok
172 | Yaqoob | Email | Starred should display with email | Suggestion | Acknowledged |  | Arsalan | [5 empty] | ok
173 | Yaqoob | Email | When I have changed my Gmail Account Password, Email Stopped syncing in Axis. ( Suggest Email should logout in Axis and display login screen in this case ) | Suggestion | Open | Critical | Arsalan | Rafhan has to do some tweaks, however, developer can work on functionality. |  |  |  |  | ok
175 | Yaqoob | Email | When deleting old draft screen not taking back/ updating the screen until refresh tha page | Bug | Re-Open |  | Hamza | It is deleting one by one, too slow process. Pls optimize.
177 | Yaqoob | Feeds | Reval Rates Date not updating | Bug | Acknowledged |  | Arsalan | [5 empty] | ok
178 | Farhat | Feeds | correct the spelling of succuss success when deleted news from admin panel. | Bug | Acknowledged |  | Arsalan
179 | Farhat | Feeds | need Ck eeditor for uploading news. complete description not show | Suggestion | Acknowledged |  | Faizan
180 | Farhat | Feeds | News on feed comes after 1 minute of notification | Suggestion | Acknowledged |  | Arsalan | [5 empty] | ok
181 | Shumaila | Feeds | auto logout account while clicking on admin panel | Bug | Ignore |  |  | It is due to the access management.
182 | Yaqoob | Feeds | Noticeboard creating horizontal scroll due to large heading. Heading should be restricted | Bug | Acknowledged |  | Rafhan
183 | Yaqoob | Feeds | Notice Board description should not be limited also Edit text component should be available | Suggestion
184 | Yaqoob | File Sync | Shared File not reflecting in real time in recents also no notification | Bug | Not Reproducible |  |  | Functional Issue
185 | Yaqoob | File Sync | OBS file format working very slow | Performance |  |  |  | NC Optimization
186 | Yaqoob | File Sync | Collabora response is very slow taking time to display the work | Performance |  |  |  | NC Optimization
187 | Yaqoob | File Sync |  | Suggestion |  |  |  | Collabora default functionality
188 | Yaqoob | File Sync |  | Suggestion |  |  |  | Collabora default functionality
189 | Yaqoob | File Sync | Sheet change functionality not working | Other |  |  |  | NC default functionality |  |  |  |  | ok
190 | Yaqoob | Feeds | Edit fields should not ask for new data and even add the data changes not updating | Other | Not Reproducible | [7 empty] | ok
191 | Yaqoob | Feeds | Delete deposit rate not working showing not executed message | Other | Not Reproducible
192 | Farhat | Feeds | Not able to attach image while creating news (Admin) | Suggestion | Open |  | Rafhan | [5 empty] | ok
193 | Farhat | Feeds | text having tables and columns alignment out, shows as plain text with no gaps (Admin) | Suggestion | Open |  | Rafhan
194 | Shoaib | Feeds | Feeds should be share to social media platforms. | [9 empty] | ok
195 | Shoaib | Feeds | As soon as user click on the x button after search, all news feeds should available.
196 | Shoaib | Feeds | All Category should be read as "News". | [9 empty] | ok
197 | Sumair | Feeds | Feed section click All-> SBP. Background should be same | Suggestion | Open |  | Rafhan
198 | Ovais | General | When open multiple browsers, click on notification should remove the counter in all the browsers/tabs. | Bug | Acknowledged |  | Arsalan
199 | Shoaib | General | Just after sign in, an usual box appear for the sign in details, credentials should be asked only once! | Bug | Acknowledged |  | Ovais | Functional Issue
200 | Ovais | General | ERR2_HTTPS_PROTOCOL_ERROR | Bug | Open |  | Ovais
201 | Sadiq | General | My system does not support axis, i have saved screen shots which errors i am facing | Bug | Acknowledged |  | Rafhan | UI functionality
202 | Iqra | General | Between the notification bell icon and the announcement ticker, there should be a clear spacing. | Suggestion | Acknowledged |  | Rafhan | TBD
203 |  | General | Scroll color should change when hover on scroll | Suggestion | Acknowledged |  | Rafhan
204 |  | General | The record should be highlighted on hover in every feature like sticky notes, file sync, calendar, feeds and others. | Suggestion | Acknowledged |  | Rafhan
205 | Shoaib | General | Overal features should be optimized, and must response rapidly. | Performance |  |  |  | Optimization |  |  |  |  | ok
206 | Shoaib | General | How to mark all notification as read at once ??
207 | Shumaila | General | auto logout account while clicking on admin panel, If admin right not given admin Panel shouldn't be displayed to user
208 | Sumair | General | Until and unless main page contents are not loaded sidebar requests should not be sent out. This will decrease the initial load time also. | Suggestion | Resolved | Critical | Fahad | Still able to click the option |  |  |  |  | ok
209 | Yaqoob | File Sync | When uploading a folder all folder files appearing on screen in mac | Bug | Open |  | Arsalan | Arsalan : UI compatibility issue
210 | Sumair | General | Lot of check chat sessions are being sent out. And this is happening at initial load also. As suggested load sidebar contents once the main page contents are loaded | Suggestion | Resolved | Critical | Fahad | The request should only be initiated once Axis completely loads. |  |  |  |  | ok
211 | Sumair | General | In case if email is opened in big size then first the file synch and calender widget are being visibly loaded and then the email widget goes into maximum size. this should not be the case | Suggestion | [8 empty] | ok
212 |  | General | Keyboard Shortcut
213 | Yaqoob | Greeting Screen | Greeting screen appearing even if setting is off by default | Bug | Acknowledged |  | Fahad | Functional Issue
214 | Sumair | Insights | CSS loading issue. sometimes css of drop downs in insight is not being loaded properly. Until and unless CSS is not loaded properly the widget should not be visible and loader should run. | Suggestion
215 |  | Internal News | News Not creating from Live | Bug | Acknowledged |  | Faizan
216 | Yaqoob | Internal News | Doubling of Notification | Bug | Acknowledged |  | Faizan
217 | Yaqoob | Internal News | On creating news 404 error appearing whereas news is generated after a few minutes. | Bug | Acknowledged |  | Faizan
218 | Yaqoob | Internal News | Please display tresmark news editor in axis admin | Bug | Open |  | Faizan
219 | Yaqoob | Internal News | Limited Title and Description should not be displayed | Suggestion | Acknowledged |  | Faizan
220 | Yaqoob | Internal News | Add attachment option in editor | Suggestion | Open |  | Faizan
221 | Yaqoob | Internal News | Delete option not working | Bug | Acknowledged |  | Faizan
222 | Yaqoob | Internal News | Editor required on edit the news same as at the time of news creation. Content must display at the time of edit. | Suggestion | Open |  | Faizan | [5 empty] | ok
223 | Yaqoob | File Sync | When create a new independent folder during moving a file folder created under a previous folder. Display on front screen just for a while | Bug | Acknowledged | [7 empty] | ok
224 | Yaqoob | Internal News | News not reflecting on real time basis. | Bug | Acknowledged |  | Faizan
225 | Yaqoob | Internal News | Internal News Design need to correct | Suggestion
226 | Yaqoob | Internal News | When delete a news. Notification created for that news, should also be removed | Suggestion
227 | Yaqoob | Video | Internet Connectivity message should display to participant if any participant internet connectivity is not stable | Suggestion | Resolved | Critical | Arsalan | Unable to check
228 | Yaqoob | Video | Audio recording option should be available | Roadmap
229 | Yaqoob | Internal News | Need Editor when edit any News / Notice board | Suggestion | Open |  | Rafhan
230 | Yaqoob | Internal News | Notice board and Internal news page Design need to be changed as similar as Tresmark | Suggestion | Open |  | Rafhan
231 | Yaqoob | Loader | Display percentage with Axis main loader
232 | Yaqoob | Video | Missed Video call should be updated in the list on real time | Suggestion
233 | Yaqoob | Video | If caller leave the call receiver should be prompted by message " Sender<Yaqoob> has left the call" | Suggestion | Resolved | Critical | Arsalan | Toast messge shown by Rafhan.
234 | Yaqoob | File Sync | If file name in other language system create folder | Roadmap
235 | Yaqoob | Login Screen | Please change login screen with all flows | Suggestion | Acknowledged |  | Arsalan |  |  | Critical
236 | FM | Markets | I continued my previous session from yesterday to today. Markets tab is not updated (Mac) | Bug | Test Again |  |  | Need to check
237 | Sumair | Markets | Markets widget Date and Time of last update should be in black color. | Suggestion | Ignore |  |  | All dates are in grey color. Ex: Kibor, and other SBP sections.
238 | Yaqoob | Media | Delete Media option should be available | Suggestion | Ignore
239 | Sumair | Media | On initial load why does Media requires 2 clicks to open. Recurring single clicks works fine. | Suggestion | Acknowledged |  | Arsalan
240 | Yaqoob | Minisite | Unable to delete the minisite even though I have deleted the department from admin site | Bug | Acknowledged |  | Faizan
241 | Yaqoob | Minisite | I dont have page creation rights but still able to create and remove pages. Only admin should have this right | Bug | Acknowledged |  | Faizan
242 | Yaqoob | Minisite | In edit bar attach image , video and file option is missing | Other | Acknowledged |  | Faizan
243 | Yaqoob | Minisite | Unable to paste image in minisite page | Other | Acknowledged |  | Fahad
244 | Yaqoob | Minisite | Some time edit content option not working | Bug | Acknowledged |  | Faizan
245 | Yaqoob | Minisite | If there is not admin right then rename page option should not be displayed | Bug | Acknowledged |  | Faizan
246 | Yaqoob | Minisite | Delete Minisite name from admin but still appearing in Minisites list | Bug | Acknowledged |  | Faizan
247 |  | Minisite | In Edit tool when ever I click edit content a new attachment icon appear on the toolbar in minisite on Safari, Chrome, Edge, Firefox , Opera |  | Acknowledged |  | Faizan
248 | Yaqoob | Minisite | Change the Document icon as implemeted on Axismain | Suggestion | Acknowledged
249 | Yaqoob | Minisite | Page title should be in the middle of the picture | Suggestion | Acknowledged
250 | Yaqoob | Minisite | When create a page in Minisite number 2 system redirect the user in minisite 1. It should stick to minisite 2 | Bug | Acknowledged
251 | Yaqoob | Minisite | When click edit content area increases and click save area decreases. Please check content area must be same | Bug | Acknowledged
252 | Yaqoob | Minisite | Talk not working on Minisite | Bug | Acknowledged |  | Hamza
253 | Yaqoob | Minisite | Minisite Not Reflecting in Real time | Suggestion | Open | Critical | Faizan | If minisite has assigned to the user, then it should appear on refresh screen.
254 | Yaqoob | Minisite | Doubling of new created ministe in the admin Minisite access management list | Bug | Acknowledged |  | Faizan
255 | Yaqoob | Minisite | Doubling of Minisite name on user end | Bug | Acknowledged |  | Faizan
256 | Yaqoob | Minisite | Doubling of Department Name in Admin page | Bug | Re-Open |  | Faizan | It is still happening.
257 | Yaqoob | Minisite | If a user already in minisite then user name must be displayed in Minisite > Access Management user name list | Suggestion | Acknowledged |  | Faizan
258 | Yaqoob | Minisite | Attachments to be displayed on blinking cursor | Suggestion | Acknowledged |  | Faizan
259 | Yaqoob | Video | When Initaite a call ,calling and ringing message should display. | Suggestion | Resolved | Critical | Hamza | Some type of message should be displayed to the caller.
260 | Yaqoob | Video | When add a participant during a video call, caller dont initimate that the call has been initiated | Suggestion | Open | Critical | Hamza
261 | Yaqoob | Video | When notification appear video screen move below | Suggestion
262 | Yaqoob | Video | When a participant leave the call notification should appear | Suggestion | Resolved |  | Arsalan
263 | Yaqoob | Video | When click on whiteboard some loader should appear for user initimation | Suggestion | Re-Open | Critical | Rafhan | Design required.
264 | Yaqoob | File Sync | Edit view rights user should have all rights | Suggestion | Acknowledged
265 | Yaqoob | File Sync | Remove Can Share option as this option is already covered in can edit | Suggestion | Acknowledged
266 | Yaqoob | Minisite | Link can be remove by using back space and then click save the changes | Suggestion | Acknowledged
267 | Yaqoob | Minisite | When ever user change the page Confirmation message for Save Changes or Discard to be displayed | Suggestion | Acknowledged
268 | Yaqoob | Minisite | Admin can give 'can view' and 'can edit' rights to any user | Suggestion | Acknowledged |  | Arsalan
269 | Yaqoob | Minisite | An admin will be able to assign another admin if he is willing to remove from any minisite / department | Suggestion | Acknowledged |  | Arsalan
270 | Yaqoob | File Sync | When Amna reshared a file ,File was not shared with Shumaila | Bug | Acknowledged |  | Danish
271 | Yaqoob | File Sync | Farhat shared a file , I edit the file, Then farhat edit the file my changes disappeared. | Bug | Acknowledged |  | Danish
272 | Yaqoob | File Sync | Shared file removed from NC but displaying in Axis | Bug | Open |  | Danish
273 | Yaqoob | File Sync | Remove word Folder in File Sync with folder. | Bug | Acknowledged |  | Arsalan
274 | Shumaila | Minisite | minisite not configured appears when change department | Bug | Open |  | Faizan
275 | Yaqoob | Minisite | admin unable to edit minisite page, editor vanish and edit content button not showing | Bug | Acknowledged |  | Faizan
276 | Yaqoob | Minisite | Minisite access managment change the rights from to edit to view and make another user admin and assign working fine till here then when we are removing old admin it is displaying the message " The person isnot admin " untill reload the page | Bug | Acknowledged |  | Arsalan
277 | Yaqoob | Minisite | In Minisite last modified date to be given. | Suggestion | Open |  | Rafhan
278 | Yaqoob | Minisite | Document should be displayed in list format as well. | Suggestion | Open |  | Rafhan
279 | Yaqoob | Minisite | Recent activity, member list, last update etc should be displayed on every minisite landing page | Suggestion | Open |  | Rafhan
280 | Yaqoob | Minisite | Axismain needs to display proper content near to real activity to be used for demos. | Suggestion | Acknowledged |  | Rafhan
281 | Yaqoob | Talk | Talk Channel Icon need to be changed | Suggestion | Open |  | Rafhan
282 | Yaqoob | Minisite | When attach a video, File and Image attachment should display as Gmail display the attachment | Suggestion
283 | Yaqoob | Minisite | Attachments like MP4, CSV file displaying error screen in HR Policy page | Bug | Open | Critical | Faizan
284 | Yaqoob | Minisite | When click on picture only picture should open in modal. | Roadmap
285 | Yaqoob | Minisite | Attachments of HR Policy page not displaying in Documents | Bug | Open | Critical | Faizan
286 | Yaqoob | Minisite | In Minisite > access management > Role Management flow need to correct | Suggestion | Open |  | Rafhan
287 | Sumair | Minisite | Minisite Data Not available message should not appear on empty page | Suggestion | Open | Critical | Faizan
288 | Sumair | Minisite | Minisite sidebar of pages. Why there is a scroll bar inspite of 2 pages only. | Suggestion | Open | Critical | Rafhan | It is in the design also.
289 | Yaqoob | News Ticker | Time format should be as same as email AM/PM. Only Hour and Minutes to display. Also when headline is long time also squeezed that should not happen | Suggestion | Acknowledged |  | Ovais
290 | Yaqoob | Video | Admin should have option to forcefully close the call for any participant | Suggestion
291 | Yaqoob | Video | If Admin browser reload then Admin must have any option to re join the call. | Suggestion
292 | Yaqoob | Notes | Notes not saving if add only numbers in decription | Bug | Acknowledged |  | Arsalan | Functional Issue
293 |  | Notes | When create new note plus icon with fonts displaying at the bottom of the container | Suggestion | Acknowledged |  | Arsalan | Open modal, input title and description and press update. Then immediately re-open that modal. You will see the double records.
294 |  | Notes | Everytime I update the note, the title is squeezing. Email also sent. | Bug | Acknowledged |  | Arsalan
295 |  | Notes | Failed operation and retry action. | Suggestion | Resolved |  | Arsalan | Unable to test as the case needs to be created.
296 |  | Notes | Creating multiple notes rapidly, system is showing slowly. Video email sent. | Bug | Acknowledged |  | Arsalan | Arsalan : sorting issue
297 |  | Notes | Delete note option and delete all notes option required as discussed with yaqoob. | Suggestion | Acknowledged |  | Rafhan
298 | Yaqoob | Notes | On scroll pointer should appear | Bug | Acknowledged
299 | Yaqoob | Notes | When create new note plus icon with fonts displaying at the bottom of the container | Bug | Acknowledged
300 | Yaqoob | Notes | Please provide delete note option | Suggestion | Acknowledged |  | Arsalan
301 | Shoaib | Notes | How to delete notes ??
302 | Yaqoob | Notes | I have deleted all notes from Next cloud folder. Axis displayign error with notes | Bug
303 | Yaqoob | Notes | Functionality not working properly video is shared | Bug
304 | Yaqoob | Notes | When there is no notes in Axis, Loading persistently appearing on the screen | Bug | Open
305 | Yaqoob | Notification | Notifications are not sync read in one browser but in another browser it is unread | Bug | Acknowledged |  | Arsalan
306 | Iqra | Notification | Notifications of three digits are not displayed entirely,even after browser size adjustments | Suggestion | Acknowledged | Critical | Arsalan | Show 99+ in case of more than 99 emails. Also decrease font size.
307 | Farhat | Notification | rcvd notification of news after unchecking notification | TBD | Discussion |  |  | This needs to be discussed.
308 | Farhat | Notification | I rcvd the notification of the news create by me when notification in unchecked | TBD | Discussion |  |  | This needs to be discussed.
309 | Farhat | Notification | notification setting not working ,uncheck all still rcvd emails news notification | TBD | Discussion |  |  | This needs to be discussed.
310 | Yaqoob | Notifications | Notifications missing for File Sync and Calendar | Bug | Acknowledged |  | Arsalan | Functional Issue
311 | Farhat | Rate Sheet | correct the spelling of succuss success when deleted | Bug | Acknowledged |  | Arsalan
312 | Yaqoob | Search | Change search design for Project in Axismain | Suggestion | Open |  | Rafhan
313 | Yaqoob | Search | Search All page to be redesigned by chronological order | Suggestion | Open |  | Rafhan
314 | Yaqoob | SideBar | Minisite to go up in place of address book, Hide address book and automate option | Suggestion | Acknowledged |  | Ovais
315 | Yaqoob | Video | When ever user left the call message should display to user that "User has left the call" | Suggestion
316 | Yaqoob | Video | When only one participant left in video call , participant screen display on half the screen | Bug
317 | Sumair | SideBar | If the video panel is opened then the mouse hover effect of sidebar icons doesn't works. | Suggestion |  |  | Rafhan
318 | Sumair | SideBar | Talk panel or video panel gets closed when i click any where in the center. This should not be the case. We should be able to keep the panel open while working on other widgets. | Suggestion | Open | Critical | Rafhan | Talk side panel and video bottom panel.
319 | Yaqoob | Snap | Windows key displaying in Mac browsers | Bug | Acknowledged
320 | Yaqoob | Talk | Some Users from recent chat disappear whereas chat with them recently | Bug | Not Reproducible |  | Hamza
321 | Yaqoob | Video | Admin should have option to forcefully close the call for any participant | Suggestion | Open |  | Danish
322 | Yaqoob | Talk | In search result Buzzed message always appearing | Bug | Acknowledged |  | Hamza
323 | Yaqoob | Talk | User send an email but user unable to see email in domain | Bug | Acknowledged |  | Hamza
324 | Yaqoob | Talk | Chat send via email but receiver did not receive the email | Bug | Not Reproducible |  | Hamza
325 | Yaqoob | Talk | In Group while adding user previous chat display check box functionality is missing. example tresmark chat | Bug | Re-Open |  | Hamza
326 | Yaqoob | Talk | I have been added in the group but no counter appeared . 1 counter appeared at side bar after ctrl F5 / Notification counter issue on talk | Bug | Acknowledged |  | Ovais
327 | Yaqoob | Talk | Made Admin to Fahad in Axis Testing group. In group Info admin name is not visible | Bug | Acknowledged |  | Hamza
328 | Yaqoob | Talk | Real time append user in one to one chat show hover abnormal. and hide all other users. / Hover should apply on all not on name only | Bug | Resolved |  | Hamza | pls discuss
329 | Yaqoob | Talk | When user added in the group without previous message rights on print chat all messages displayed to user | Bug | Acknowledged |  | Hamza
330 | Kazim | Talk | User should be alerted with tone when receive a new message in talk | Suggestion | Open |  | Ovais | Tweak
331 | Kazim | Talk | If user share link in talk, link not visible to user due blue color background | Bug | Acknowledged |  | Ovais | Tweak
332 | Yaqoob | Talk | When initiate group video call in Talk and then leave the call Camera still open | Bug | Open |  | Ovais | Functional - To be checked
333 | Shoaib | Video | As soon as someone reject the call the video panel display some message (i.e. Redial, Dimiss or etc.)
334 | Shoaib | Video | Leave Call Alert should not be there if already move on to another call.
335 | Shoaib | File Sync | File size restrictions should be apply on file/folder uploading, as currently users can even upload windows image file and stuck on loader.
336 | Yaqoob | Talk | While creating a group, when add a member in a group by tick a user, list of users disappear | Bug | Acknowledged |  | Ovais | Functional Issue
337 | Yaqoob | Talk | Last post sharing time appearing in some Room and in some Room it is blank | Bug | Acknowledged |  | Ovais | Functional Issue
338 | Shoaib | File Sync | Folders are not created whenever user add special character in folder name.
339 | Yaqoob | Talk | When share any file from file sync to Talk, Title not visible ( may be due to blue color) | Bug | Acknowledged |  | Ovais | Functional Issue
340 | Waqas | Talk | Sometime doubling of Talk message | Bug | Re-Open |  | Ovais | Optimization
341 | Waqas | Talk | Notification not stable, group notification | Bug | Acknowledged |  | Ovais | Functional Issue
342 | Yaqoob | Talk | While creating a group, when add a member by searching a word system not allowing to select multiple user by that search word | Bug | Acknowledged |  | Ovais
343 | Kazim | Talk | Share multiple messages to single user. | Suggestion | Open |  | Rafhan | TBD
344 | Yaqoob | Talk | Delete Group Option should be available | Suggestion | Open |  | Hamza | Will cover with UI/UX.
345 | Waqas | Talk | Overall font formatting should be same | Other | Open |  | Hamza | Part of UI/UX
346 | Kazim | Talk | Tab notification should display user name in tab | Roadmap | Open | Critical
347 | Kazim | Talk | Online and offline contact filter should be available | Roadmap | Open | Critical
348 | Kazim | Talk | When internet disconnect user status becomes offline, even after internet connect again | Bug | Not Reproducible |  |  | Functional Issue
349 | Kazim | Talk | Video call option is missing in all tabs | Roadmap | Open | Critical
350 | Asif | Talk | I send an attachment on Talk after sending an attachment , chat is not working. | Bug | Not Reproducible |  |  | Functional Issue
351 | Asif | Talk | Attachment cancellation or delete option is not showing | Bug | Not Reproducible |  |  | Functional Issue
352 | Asif | Talk | I am sending an attachment to Mr Yaqoob but sent to Faisal Sb after opening the new chat box of Faisal Sb | Bug | Not Reproducible |  |  | Optimization
353 | Asif | Talk | Attachment Late receiving. | Performance |  |  |  | Optimization
354 | Yaqoob | Talk | During loading in attachment user type a message and click send message displaying in recent option but not in chat box | Performance |  |  |  | Functional Issue
355 | Farhat | Talk | file cant attached or sent | Bug | Not Reproducible |  |  | Functional Issue
356 | Farhat | Talk | chat not appeared in recent when attachd any file (PDF,XLs) .show previous chat of new user ,need to add this chat again | Performance |  |  |  | Optimization
357 | Iqra | Talk | Green dot that indicates the chat is active, shown left side of the user icon | Suggestion | Acknowledged |  |  | TBD
358 | Iqra | Talk | Can't shared attachments via chat | Performance | Not Reproducible |  |  | Performance
359 | Farhat | File Sync | Star functionality not working properly | Bug | Open | Critical | Arsalan
360 | Farhat | File Sync | when you open new folder ,folder name not visible | Bug | Ignore
361 | Farhat | File Sync | cant open new folder directly in new tab if empty or not ,can only open whatever is inside it. | Bug | Acknowledged | Critical | Arsalan | If no record found, then message to be shown.
362 | Farhat | File Sync | Cannot share new folder but can share it on NC | Roadmap | Open | Critical |  | Functionality not implemented for sharing folder.
363 | Iqra | Talk | Recent chats are not working, some have suddenly disappeared. | Performance | Not Reproducible |  |  | Performance
364 | Yaqoob | Talk | Recent, Chat , one to one chats, group chat etc scroll not working. Unable to see old chats | Bug | Acknowledged |  | Hamza
365 | Yaqoob | Talk | When Remove All user from group system donot save changes. | Bug | Acknowledged |  | Hamza
366 | Yaqoob | Talk | Hide video icon in Talk where not implemented yet | Suggestion
367 | FM | Talk | Need to change emoticons | Suggestion | Open | Critical | Rafhan
368 | FM | Talk | Is there any way I can see info on any individual group message | Suggestion | Open | Critical | Hamza
369 | FM | Talk | Other point: Clicking anywhere hides the Talk panel. Talk panel should be available at all times unless manually hidden. Even if I use another button in side panel (e.g. apps or plugins, etc | Roadmap | Resolved | Critical | Fahad | Duplicate of 318.
370 | Yaqoob | Talk | When forward a message, chat box should changed with forwarded user | Suggestion | Acknowledged |  | Rafhan
371 | Yaqoob | Talk | Talk counter abnormal in fahad system screen shot has been shared | Bug | Open | Critical | Ovais
372 | Yaqoob | File Sync | Axis is in consistent in performing opertaion like upload a file in a folder, moving the file from next clould but axis not properly sync, Rename a folder it changes the folder format etc whereas Web and Next cloud folder in system are properly sync | Suggestion | Open | Critical | Fahad | The feature has assigned to Fahad in a timelines.
373 | Yaqoob | Talk | When send a message , send message should delivered to user with timer | Suggestion | Open |  | Hamza | With UI/UX
374 | Yaqoob | Talk | On change an admin message should display | Suggestion
375 | Yaqoob | Talk | When a participant left/ added in the group message should be dipslayed | Suggestion
376 | Yaqoob | Talk | Multiple admin option should be available | Suggestion | Resolved | Critical | Rafhan | Yaqoob, please elaborate.
377 | Yaqoob | Talk | When follower share something in public room user get the email notification. Current not getting any email notification | Suggestion
378 | Yaqoob | Talk | Hashtag word should not be upper and lower case sensitive | Suggestion | Open |  | Hamza | With UI/UX
379 | Shoaib | Talk | Other languages fonts are not supported basically question marks are text in other language
380 | FM | Talk | Axis testing group missing in recent chat
381 | Iqra | Talk | Some of my previous chats are missing | Bug | Open | Critical | Hamza
382 | Asif | Talk | I create chat group but if i want to delete that group there are not any options for deleting that chat group. | Suggestion | Open | Critical | Hamza
383 | Farhat | Talk | not able to use (") also in group name | Suggestion | Open | Critical | Hamza
384 | Farhat | Talk | chat and group disappeard when i leave the group and make someone admin ( Group should not be removed) | Suggestion | Open | Critical | Hamza
385 |  | Talk | system removing the option of previous message display when try to add the user again (Reoccur ref 237)
386 | Yaqoob | Talk | Main Search and Noticeboard panel should appear over Talk, When Talk panel is open | Suggestion | Open |  | Rafhan
387 |  | Talk | Axismain edit group need to redesign |  |  |  | Rafhan
388 |  | Talk | When user press tab on any id from suggestion. System display double IDs |  |  |  | Rafhan
389 |  | Talk | When user select id from suggestion and click enter , cursor dont appear |  |  |  | Rafhan
390 | FM | Talk App | Click on pdf file a alert message appeared. Ref: Axis testing group date 12 Aug (Iphone) | Bug | Open |  | Jawwad | Assigned to Jawwad
391 | FM | Talk App | Why Image starting to load all the time when clcik on chat (Iphone) | Bug | Open |  | Jawwad | Assigned to Jawwad
392 | FM | Talk App | Can’t see who all are in this group. On app (Iphone) | Suggestion | Open | Critical | Jawwad
393 | FM | Talk App | Sending thumbs up converts to 2 ? Emoticon not supporting in App (Iphone) | Suggestion | Open | Critical | Jawwad | It will be incorporated with Axis App.
394 | FM | Talk App | Couldn’t forward image to 3rd party (Iphone) | Roadmap | Open | Critical
395 | FM | Talk App | User not sign in message appear in app, when login
396 | FM | Talk App | When click on notification first time when open app, app becomes crash
397 | Yaqoob | User Profile | DP picture resolution is not appropriate in Chrome, Edge , Opera in windows | Suggestion
398 | Yaqoob | User Profile | When Disable all Notification then all notification option should be disable same as for Enable all notification | Suggestion
407 | Yaqoob | Video | On minimize showing a square box that is not the correct design. | Bug | Resolved | Critical | Arsalan | This is due to change in css by rafhan bhai
408 | Sumair |  | Loader on Markets widget is not coming in center of markets widget. | Suggestion | Acknowledged |  | Arsalan
409 | Yaqoob | Minisites | Loader should not appear on loading minisite page
410 | Fahad | Video | Recent and Missed video call history should be fetched in a single call, and on click of video icon only. If the history is already loaded before, then do not load it again from DB, just show it. | Performance | Re-Open |  | Arsalan
411 | Fahad | Address Book | GetAddressBookData() is not using right now as we are not showing Address book. Comment out this method from client side. | Performance | Resolved |  | Arsalan
412 | Fahad | Video | UserListForVideoCall() is searching data from DB. It should be from the user collection. | Performance | Open |  | Arsalan
413 | Fahad | Social Media | SocialData() is calling on document ready. It should be on click of Social Media icon. | Performance | Resolved |  | Hamza
414 | Fahad | Markets | GetCommodities(), GetGlobalIndices() and GetCurrencies() taking more than 5 seconds. Find ways to reduce this time. | Performance | Resolved |  | Arsalan
415 | Fahad | Calendar | GetUsersForCalendar() method also fetching users from DB. It should be from the user collection. | Performance | Ignore |  | Arsalan
416 | Fahad | Email | GetEmailPartialList() method is calling twice. Why? Load only Inbox on document load. | Performance | Resolved |  | Hamza
417 | Fahad | Greeting Screen | Greeting modal should show immediately after main axis loader disappears. It should show everytime. Comment out the functionality of showing it once in a day. | Performance | Resolved |  | Fahad
418 | Fahad | Markets | Markets data on single request + showing 2 decimal places initially, and then actual ones | Performance | Open
419 | Yaqoob | Notification | Notifications DP with Icons. Please update the icons as implemented on Search. Also remove menu icon | Suggestion | Open |  | Rafhan
| Sumair | Minisite | Custom file name mechanism to be incorporated while attaching any file in editor. | Suggestion | Open |  | Faizan
| Yaqoob | General | Email disconnectivity message in Axis same as Tresmark
| Iqra | File Sync | If a folder name AXIS*, so due to asteric feature stuck on loading
| Iqra | Notes | When there is no notes , Features axis on loading when login on Axis
|  |  | Recent call status not updating on realtime | Bug | Resolved |  | Arsalan
| Yaqoob | Email | email widget hover dropdown issue. On last email hover is showing on scroll | Bug |  |  | Rafhan
| Ovais | Email | Email list scrolling shows 3 dots with pagination icons. | Bug | Open |  | Arsalan | It is not happening in axis main.
|  | Minisite | Minisite home page needs to implement. | Suggestion | Open |  | Faizan
|  | Minisite | Axis loader and greetings screen not need to be shown on minisite. | Suggestion | Open |  | Faizan
|  | Minisite | Minisite not loading pages. | Bug | Open | Critical | Faizan
|  | Project | Projects: Instruction on landing page | Suggestion | Open | Critical | Rafhan
|  | Project | Projects: In board view to give create task oprion in every column | Suggestion | Open | Critical | Rafhan
|  | Project | Projects: Need to give Custom category option while creating the task | Suggestion | Open | Critical | Rafhan
|  | Project | Projects: Expand and Collapse option required in Kanban view | Suggestion | Open | Critical | Rafhan
|  | Project | Projects: Left panel expand and collapse option | Suggestion | Open | Critical | Rafhan
|  | Project | Projects: In report format need to display variance aswell | Suggestion | Open | Critical | Rafhan
|  | Project | Project talk group will create at the time of click at talk icon | Suggestion
|  | Project | Projects: Tooltips should be available on icons beside search | Suggestion | Open | Critical | Rafhan
|  | Project | Projects: Task Breakup is a task takes more than 8 hours | Roadmap
|  | Search | In Search display accurate time and Content in axis main | Suggestion | Open |  | Rafhan
|  | Search | While user search a word, user should intimate with color | Suggestion | Open |  | Rafhan
|  | Search | Talk will also be added in generic Search | Roadmap | Open |  | Rafhan
|  | Notes | Need to give attachement option in Notes | Suggestion | Open |  | Rafhan
|  | SideBar | Active Directory to unhide without Talk and Video | Suggestion | Open |  | Rafhan
|  | Search | In Search page navigation design to be change | Suggestion | Open | Critical | Rafhan
|  | General | Main loader improvement | Suggestion | Open | Critical | Rafhan
Note on F11: Still creating multiple records with same logged in time -Muhammad Yaqoob
Note on F21: In consistent behavior sometime working sometime not -Muhammad Yaqoob
Note on F116: White board not working -Muhammad Yaqoob @hamza@landmark-investment.com will look this -Fahad Hasan
Note on F147: Correct ID not getting email also not displaying sent box -Muhammad Yaqoob
Note on F149: for how many mail ? for example I opened 50 emails a day. so among 50 how many emails you want to not show loader Second it might affects the performance so I can do RND on this -Fahad Hasan
Note on F152: Done all methods changed now junk not junk delete not delete not star read unread. all methods now will be done on single click, Further more undo from trash also hit back and update counter to 25 again. -Fahad Hasan
Note on F154: Scroll changing the cursor icon after implement the scroll functionality. -Muhammad Yaqoob
Note on F159: System stuck on loading that should not happen. -Muhammad Yaqoob Also there is not toast message displaying -Muhammad Yaqoob
Note on F165: There is no toast message -Muhammad Yaqoob
Note on F178: Still taking time -Muhammad Yaqoob
Note on I187: @ovais@landmark-investment.com Cant we consider a bug from NC ? -Muhammad Yaqoob Yes. -Muhammad Ovais
Note on F216: In editor alignments option not working properly -Muhammad Yaqoob
Note on F254: Still Occurring -Muhammad Yaqoob
Note on F272: Minisite not Configured appears until user logout and login again that should not happen -Muhammad Yaqoob
Note on F305: Sent email displaying in send box -Muhammad Yaqoob
Note on F323: Still not appearing the option -Muhammad Yaqoob When adding user without given previous chat option user still able to see previous chat. Also now able to given option to display previous chat -Muhammad Yaqoob
Note on F327: But when user added with previous chat display rights Talk displaying only messages after added in the group -Muhammad Yaqoob
Note on F363: But system removing the option of previous message display when try to add the user again -Muhammad Yaqoob

## Summary
Category (H) | Count
Bug | 142
Other | 12
Performance | 8
Roadmap | 29
Suggestion | 153
Grand Total | 344
Category (H) | Bug
Bugs
Status (I) | Count
Acknowledged | 95
Ignore | 3
Not Reproducible | 15
Open | 18
Re-Open | 7
Resolved | 4
Test Again | 1
(blank)
Grand Total | 143
Category (H) | Bug
Bugs
Count | Status (I)
Resource | Not Reproducible | Open | Resolved | Grand Total
Arsalan |  | 2 | 1 | 3
Danish |  | 4 |  | 4
Hamza | 5 | 1 | 3 | 9
Ovais |  | 3 |  | 3
Rafhan |  | 1 |  | 1
Grand Total | 5 | 11 | 4 | 20
Category (H) | Bug
Status (I) | (Multiple Items)
Bugs
Area
Audit Trial
Axis API
File Sync
General
Internal News
Minisite
Notes
Talk
Talk App
Video
Grand Total
Critical
COUNT of S. No. | Status (I)
Category (H) | Acknowledged | Open | Re-Open | Resolved | Grand Total
Bug | 3 | 3 |  | 1 | 7
Roadmap |  | 8 |  |  | 8
Suggestion | 2 | 14 | 1 | 6 | 23
Grand Total | 5 | 25 | 1 | 7 | 38
Resource
Severity | Critical
Status (I) | (Multiple Items)
Category (H) | (Multiple Items)
Area | (Multiple Items)
Resource | COUNT of S. No.
Arsalan | 3
Danish | 2
Fahad | 2
Faizan | 4
Hamza | 1
Jawwad | 2
Rafhan | 4
Grand Total | 18

## Asif (hidden)
S. No. | Area | Observation/Description/ Steps to reproduce | Category | Developer | Status | Remarks | Area | Resource | Status
| Email | unable to find editing tools on the main screen of compose email. |  |  |  |  | Access Management | Arsalan | Open
| Email | When i enter the next line, Space showing between the line |  |  |  |  | Address Book | Danish | Resolved
| Email | When I click format tools pen, there are not showing up Remove formatting and Undo Redo tools |  |  |  |  | Authorization | Fahad | Tested
| Email | No notification of new email
| Talk | I send an attachment on Talk after sending an attachment , chat is not working. |  |  |  |  | Calendar | Hamza | Acknowledged
| Talk | Attachment cancellation or delete option is not showing |  |  |  |  | Daily Digest | Ovais | Re-Open
| Talk | I am sending an attachment to Mr Yaqoob but sent to Faisal Sb after opening the new chat box of Faisal Sb |  |  |  |  | Email |  | Ignore
| Talk | Attachment Late receiving. |  |  |  |  | Feeds |  | Discussion
| Calendar | When I update an event on Calendar, not showing me any notification that it is updated. |  |  |  |  | File Sync
| Calendar | Reminder not working |  |  |  |  | Greeting Screen
Insights
Markets
Media
News Ticker
Notes
Notifications
Settings
Talk
User Profile
User Status
Video
Deposit Sheet
Rate Sheet
General
Internal News

## Iqra (hidden)
S. No. | Area | Observation/Description/ Steps to reproduce | Category | Developer | Status | Remarks | Area | Resource | Status
| Talk | Green dot that indicates the chat is active, shown left side of the user icon |  |  |  |  | Access Management | Arsalan | Open
| Email | All categories except Inbox, including Sent item and Draft are empty, previous emails are not replicated. |  |  |  |  | Address Book | Danish | Resolved
| Email | While composing a new email, the system should suggest the id's of people with whom I've already communicated. I have to write whole email address |  |  |  |  | Authorization | Fahad | Tested
| Talk | Can't shared attachments via chat |  |  |  |  | Calendar | Hamza | Acknowledged
| Talk | Recent chats are not working, some have suddenly disappeared. |  |  |  |  | Daily Digest | Ovais | Re-Open
| General | Between the notification bell icon and the announcement ticker, there should be a clear spacing. |  |  |  |  | Email |  | Ignore
[7 empty] | Feeds |  | Discussion
File Sync
Greeting Screen
Insights
Markets
Media
News Ticker
Notes
Notifications
Settings
Talk
User Profile
User Status
Video
Deposit Sheet
Rate Sheet
General
Internal News

## Yaqoob
Date | Area | Observation/Description/ Steps to reproduce | Category | Developer | Status | Remarks | Area | Resource | Status | Category
| Greeting Screen | Greeting screen appearing even if setting if off by default |  |  |  |  | Access Management | Arsalan | Open | Bug
| Email | Popup should appear on any activity like incoming or outgoing emails etc |  |  |  |  | Address Book | Danish | Resolved | Suggestion
| Email | Loader should not appear while activity is being performed by system. |  |  |  |  | Authorization | Fahad | Tested
| Email | Multiple email selection option should be available |  |  |  |  | Calendar | Hamza | Acknowledged
| Talk | When initiate group video call in Talk and then leave the call Camera still open |  |  |  |  | Daily Digest | Ovais | Re-Open
| Talk | When add a member in a group by tick a user list of users disappear |  |  |  |  | Email |  | Ignore
| Talk | During loading in attachement user type a message and click send message displaying in recent option but not in chat box |  |  |  |  | Feeds |  | Discussion
| Talk | When create group/ room display at the bottom of the list |  |  |  |  | File Sync
| Talk | Last post sharing time appearing in some Room and in some Room it is blank |  |  |  |  | Greeting Screen
| Talk | Delete Group Option should be available |  |  |  |  | Insights
| Email | Recurring: After optimization perform reply all system giving space between IDs and also repeating IDs |  |  |  |  | Markets |  |  | Recurring
| File Sync | Shared File not reflection real time in recents also no notification |  |  |  |  | Media |  |  | Recurring
| Notes | Notes not saving if add only numbers in decription |  |  |  |  | News Ticker
| File Sync | When share any file from file sync to Talk, Title not visible ( may be due to blue color) |  |  |  |  | Notes
| File Sync | OBS file format working very slow |  |  |  |  | Notifications
| Email | Need to remove double arrow and setting option when user Replying all the email. |  |  |  |  | Settings
| Notifications | Notifications missing for File Sync and Calendar |  |  |  |  | Talk |  |  | Recurring
| File Sync | Shared file disappear from recent tab after open in collabora |  |  |  |  | User Profile
| File Sync | Download all files started when open any file in nc |  |  |  |  | User Status
| File Sync | Collabora response is very slow taking time to display the work |  |  |  |  | Video
| File Sync | Please remove below row that showing shared file details |  |  |  |  | Deposit Sheet
| File Sync | Unable to understand the to use case of insert mode and standard selection pls hide |  |  |  |  | Rate Sheet
| File Sync | Sheet change functionality not working |  |  |  |  | General
| File Sync | When ever click a file, File should open not NC page |  |  |  |  | Internal News
| Email | Displaying x on start of Email ID when email send to user |  |  |  |  | Minisite
|  | Collabora not working pls check |  |  |  |  | Audit Trial
| Email | Next and Previous email option should be available when user has opened an email.
| Notifications | Notifications are not sync read in one browser but in another browser it is unread
| Email | Address not found email not received in axis email
| File Sync | File not uploading in safari
| File Sync | When uploading a folder file sync tool stuck on loading in mac
| File Sync | When uploading a folder all folder files appearing on screen in mac
| Email | IF To, CC ID are wrong and bcc email is right system not sending the email to the correct ID also email failure email did not receive
| Feeds | Noticeboard creating horizontal scroll due to large heading. Heading should be restricted
| Email | In draft menu delete option alignment is not accurate
| Email | Please remove setting and double arrow in sign in screen
| Email | Trash email not synced 24-Nov-2021
| Minisite | Unable to delete the minisite even though I have deleted the department from admin site |  |  | Resolved | Bug
| Minisite | Change the Document icon as implemeted on Axismain |  |  | Resolved | Not Bug
| Minisite | Page title should be in the middle of the picture |  |  | Resolved | Not Bug
| Minisite | When create a page in Minisite number 2 system redirect the user in minisite 1. It should stick to minisite 2 |  |  | Resolved | Not Bug
| Minisite | I dont have page creation rights but still able to create and remove pages. Only admin should have this right |  |  | Resolved | Bug
| Minisite | In edit bar attach image , video and file option is missing |  |  | Resolved | Not Bug
| Minisite | Unable to paste image in minisite page |  |  | Open | Not Bug
| Minisite | Some time edit content option not working |  |  | Resolved | Not Bug
| Minisite | If there is not admin right then rename page option should not be displayed |  |  | Resolved | Duplicate
| Minisite | When click edit content area increases and click save area decreases. Please check content area must be same |  |  | Resolved | Bug
| Audit Trial | Only login in admin panel but login user displaying as login
| Audit Trial | In user login history remove device ID if we can not record
| Audit Trial | In user login history most of the record are not correct repeating records in logged in time.
| Audit Trial | In user login history decrease records size like 80% screen
| Audit Trial | In user login logsrecords exceeding "to Time" range
| Audit Trial | Delete Minisite name from admin but still appearing in Minisites list
| News Ticker | Time format should be as same as email AM/PM. Only Hour and Minutes to display. Also when headline is long time also squeezed that should not happen |  |  | Resolved
| Talk | Recent, Chat , one to one chats, group chat etc scroll not working. Unable to see old chats
| Sidebar | Minisite to go up in place of address book, Hide address book and automate option |  |  | Resolved
| Email | Remove borders with attachments
| File Sync | When create a new independent folder during moving a file folder created under a previous folder. Display on front screen just for a while
| Notes | On scroll pointer should appear
| Notes | When create new note plus icon with fonts displaying at the bottom of the container
| Calendar | When adding attendees suggestion box is so stretched
| Calendar | By default all events are creating on All day
| Calendar | Event Title field should be mandatory
| Video | Multiple click option not working when trying to create group call
| Video | New Call notification donot appear when user on other or minimize the browser.
| Minisite | In Edit tool when ever I click edit content a new attachment icon appear on the toolbar in minisite on Safari, Chrome, Edge, Firefox , Opera
| Email | Star functionality not working properly
2021-12-15
| Email | Read Email displaying in Unread randomly | Bug
| Feeds | Notice Board description should not be limited also Edit text component should be available | Suggestion
| Feeds | Edit fields should not ask for new data and even add the data changes not updating | Bug
| Feeds | Delete deposit rate not working showing not executed message | Bug
| Feeds | Reval Rates Date not updating | Bug
| Email | Loader should not appear on the email that already opened /read | Suggestion
| Email | Email timing to be crossed checked again | Suggestion
| Talk | When forward a message, chat box should changed with forwarded user | Suggestion
| Talk | Some Users from recent chat disappear whereas chat with them recently | Bug
| Talk | Talk counter abnormal in fahad system screen shot has been shared | Bug |  |  | It was a previous bug, removed the counter manually on case to case basis.
| Talk | In search result Buzzed message always appearing | Bug
| Talk | When send a message , send message should delivered to user with timer | Suggestion
| Talk | User send an email but user unable to see email in domain | Bug
| Talk | Chat send via email but receiver did not receive the email | Bug |  |  | It is related to email qouta
| Talk | In Group previous chat display functionality is missing | Bug
| Talk | On change an admin message should display | Suggestion
| Talk | When a participant left/ added in the group message should be dipslayed | Suggestion
| Talk | I have been added in the group but no counter appeared . 1 counter appeared at side bar after ctrl F5 | Bug
| Talk | Unable to paste SS in group. Happening only in my system | Bug
| Talk | Made Admin to Fahad in Axis Testing group. In group Info admin name is not visible | Bug
| Talk | Multiple admin option should be available | Suggestion
| Talk | Real time append user in one to one chat show hover abnormal. and hide all other users. | Bug
| Talk | When follower share something in public room user get the email notification. Current not getting any email notification | Suggestion
| Talk | When user added in the group with not previous message rights on print chat all messages displayed to user | Bug
| Talk | Hashtag word should not be upper and lower case sensitive | Suggestion
| Video | When Initaite a call dialing tone should ring | Suggestion
| Video | When add a participant during a video call, caller dont initimate that the call has been initiated | Suggestion
| Video | When initiater leave the call video call should be closed for all participant | Suggestion
| Video | When notification appear video screen move below | Suggestion
| Video | When a participant leave the call notification should appear | Suggestion
| Video | Lagging in voice transferring | Optimization
| Video | already on call and try to initiate another call and cancel my desicion than side bar and leave call buttons will hide on current call | Bug
| Video | If user is already on call and someone call him then modal doesnot show who is calling. and when he rejects the call modal is not closing. | Bug
| Video | Left Participant also getting whiteboard notification with full control | Bug
| Video | When click on whiteboard some loader should appear for user initimation | Suggestion
| Video | All participant names not displaying in whitboard 4:03 | Bug
| Video | Changes not saved in whoteboard displaying blank screen 3:51 | Bug
| Video | NC icon appearing in i frame when click on user image | Suggestion
| File Sync | View only right user should not be able to have edit, download and share option both in NC and Axis | Bug
| File Sync | Edit view rights user should have all rights | Suggestion
| File Sync | Remove Can Share option as this option is already covered in can edit | Suggestion
| File Sync | When Amna reshared a file ,File was not shared with Shumaila | Bug
| File Sync | Farhat shared a file , I edit the file, Then farhat edit the file my changes disappeared. | Bug
| File Sync | Shared file removed from NC but displaying in Axis | Bug | Danish | Open
| File Sync | Remove word Folder in File Sync with folder. | Bug | Arsalan | Open
18 Decemeber 2021
| Media | Delete Media option should be available
| Notes | Please provide delete note option
| User Profile | DP picture resolution is not appropriate in Chrome, Edge , Opera in windows
| Minisite | Talk not working on Minisite
| User Profile | When Change password without adding Current password,Message should display that " Kindly add current password to create new password"
| User Profile | When Disable all Notification then all notification option should be disable same as foe Enable all notification
2021-12-20
| Email | When delete few news from Email system donot auto load next email to balance the 25 counter in every dropdown option | Suggestion
| Minisite | Minisite Not Reflecting in Real time
| Minisite | Double of new created ministe in the admin Minisite access management list
| Calendar | Calendar Invititation confirmation option is missing
| Calendar | Unable to click on event to view details
| Minisite | Doubling of Minisite
| Minisite | Doubling of Department Name
| Minisite | If a user already minites then user name must be displayed in Minisite > Access Management user name list
| Minisite | New Created role not showing in claims
| Minisite | View only claims are missing
2021-12-21
| Video | Admin should have option to forcefully close the call for any participant
| Video | If Admin browser reload then Admin must have any option to re join the call.
| Search | Change search design for Project in Axismain | Suggestion | Rafhan | Open
2021-12-23
| Minisite | Attachments to be displayed on blinking cursor
| Minisite | Link can be remove by using back space and then click save the changes
| Minisite | When ever user change the page Confirmation message for Save Changes or Discard to be displayed
| Minisite | 5 Attachements can only be displayed in one row
| Minisite | Multiple minisite can be assign to user but user will be admin of one minisite only
| Minisite | Admin can give 'can view' and 'can edit' rights to any user
| Minisite | In can edit rights user can perform any task that admin can do except make an admin to other user
| Minisite | An admin will be able to assign another admin if he is willing to remove from any ministe / department
2021-12-21
| Video | When ever user left the call message should display to "User that User has left the call"
| Video | When only one participant left in video call , participant screen display on half the screen
| Internal News | Internal News Design need to correct | Suggestion | Rafhan
| Email | Unable to link directly from email
| Email | Right click paste option not working where as ctrl +V is working during compose an email
| Email | Axis Internal Usage email could not send from Axis Email.
2021-12-31
| Internal News | When delete a news. Notification created for that news should also be removed
2022-04-01 | Email | Axis Email sync Functionalities with its exchange should be configurable by user end
| Email | Reset password screen need to be designed

## Sadiq (hidden)
S. No. | Area | Observation/Description/ Steps to reproduce | Category | Developer | Status | Remarks | Area | Resource | Status
|  | My system does not support axis, i have saved screen shots which errors i am facing |  |  |  |  | Access Management | Arsalan | Open
|  | 2021-12-28 |  |  |  |  | Address Book | Danish | Resolved
[7 empty] | Authorization | Fahad | Tested
[7 empty] | Calendar | Hamza | Acknowledged
[7 empty] | Daily Digest | Ovais | Re-Open
[7 empty] | Email |  | Ignore
[7 empty] | Feeds |  | Discussion
File Sync
Greeting Screen
Insights
Markets
Media
News Ticker
Notes
Notifications
Settings
Talk
User Profile
User Status
Video
Deposit Sheet
Rate Sheet
General
Internal News
Note on C2: @Sadiq.Ali@landmark-investment.com , pls share screenshots in email. _Assigned to Sadiq Ali_ -Muhammad Ovais

## Farhat (hidden)
S. No. | Area | Observation/Description/ Steps to reproduce | Category | Developer | Status | Remarks | Area | Resource | Status
| Email | old sent item not synced |  |  |  |  | Access Management | Arsalan | Open
| Email | new email not shown as updated in my gmail inbox need to refresh it |  |  |  |  | Address Book | Danish | Resolved
| Email | no notification of new email |  |  |  |  | Authorization | Fahad | Tested
| Email | reply to email in sent items not shown as updated in gmail account |  |  |  |  | Calendar | Hamza | Acknowledged
| Talk | file cant attached or sent |  |  |  |  | Daily Digest | Ovais | Re-Open
| Talk | chat not appeared in recent when attachd any file (PDF,XLs) .show previous chat of new user ,need to add this chat again |  |  |  |  | Email |  | Ignore
|  | 2021-12-15 |  |  |  |  | Feeds |  | Discussion
| Feeds | complete description not show |  |  |  |  | File Sync
| Feeds | not able to attach image |  |  |  |  | Greeting Screen
| Feeds | News on feed comes after 1 minute of notification |  |  |  |  | Insights
| Feeds | text having tables and columns alignment out, shows as plain text with no gaps |  |  |  |  | Markets
| Feeds | correct the spelling of succuss success when deleted news from admin panel. |  |  |  |  | Media
| Rate Sheet | correct the spelling of succuss success when deleted |  |  |  |  | News Ticker
Notes
Notifications
Settings
Talk
User Profile
User Status
Video
Deposit Sheet
Rate Sheet
General
Internal News

## Shoaib (hidden)
Area | Observation/Description/ Steps to reproduce | Category | Developer | Status | Remarks | Area | Resource | Status
General | Just after sign in, an usual box appear for the sign in details, credentials should be asked only once! |  |  |  |  | Access Management | Arsalan | Open
General | Overal features should be optimized, and must response rapidly. |  |  |  |  | Address Book | Danish | Resolved
Email | Just after the configration email, the email widget section shouldn't be just blank. |  |  |  |  | Authorization | Fahad | Tested
Email | Tool tip for compose the new email should be read as "Compose an email" or "New Message" instead of "New". |  |  |  |  | Calendar | Hamza | Acknowledged
Email | Email folders should be synchronize (i.e. Inbox, Sent, Draft & etc.) |  |  |  |  | Daily Digest | Ovais | Re-Open
Email | How to select all emails to do delete, unread and mark read??? |  |  |  |  | Email |  | Ignore
Email | Name of the email sender should be displayed at the time, and it shouldn't cropped. |  |  |  |  | Feeds |  | Discussion
Email | Newly received email should be correctly display mail subject and mail body(trimmed to a single line). |  |  |  |  | File Sync
Email | Whenever tried to open an email, it takes too much time. |  |  |  |  | Greeting Screen
Email | As soon as mouse pointer hover on the attachments it should change or reflect that attachment can be downloadable. |  |  |  |  | Insights
Email | Attachments should scanned for viruses before download. |  |  |  |  | Markets
Email | Navigation on email pages should optimize. |  |  |  |  | Media
Email | Count of unread emails should displayed alongside ‘Inbox’ text. |  |  |  |  | News Ticker
Email | It should possible to directly navigate to all the folders of email, regardless the current position. (Currently if the user reading an email then it is not possible to navigate to send item or any other folder). |  |  |  |  | Notes
Email | Unread email count should increase by one on receiving a new email. |  |  |  |  | Notifications
Email | Unread email count should decreases by one on reading an email (marking an email as read). |  |  |  |  | Settings
Email | Emails should be hilighted once click on "Mark as Unread" |  |  |  |  | Talk
Email | User must get suggestions while typing the email ids based on the existing email ids in user’s email list. |  |  |  |  | User Profile
Email | User can enter multiple comma-separated email ids in ‘To’, ‘cc’ and ‘bcc’ sections. |  |  |  |  | User Status
Email | User can only add email id in Recipients Text Field, it should ont be possible to send email if user add anyother text instead of email id. |  |  |  |  | Video
Email | How to add single or multiple signatures?? |  |  |  |  | Deposit Sheet
Email | How to add picture(s) in the email body ??? |  |  |  |  | Rate Sheet
Email | Email pane stuck just after save and exit. |  |  |  |  | General
Email | As soon as user click on the send button, alert message should be there to refelct the status of the email (i.e. Sending...... and Message Sent) |  |  |  |  | Internal News
Email | Undelivered mail status not available in any form.
Email | clicking ‘Send’ button, mail should deliver to intended receivers.
Email | How to add multiple email address rapidly without using mouse buttons or enter key???
Email | Semi colon can be use to seperate multiple email id(s).
Email | Add the same email id two or more times then click on the send button, check the inbox of that id, it should be mention only once at TO field.
Email | Whenever user try to send email without subject or empty body then an alert message should be there as *Send this message without a subject or text in the body?*
Email | It should be possible to send maximum number of emails at once. (By adding multiple Recipients, CC & BCC)
Email | Whenever user add multiple Recipents, then layout of the email shouldn't be inappropiate.
Feeds | Feeds should close by the cross button only.
Feeds | Feeds should be share to social media platforms.
Feeds | How to select only news feeds? currently notices from the noticeboard are there.
Feeds | As soon as user click on the x button after search, all news feeds should available.
Calendar | Whenever user select day, month and year it should reflect the day time slots, month days and calender months respectively
Calendar | It shouldn't be possible to create an event with Title.
Feeds | All Category should be read as "News".
Calendar | Events reminders are not working.
Calendar | All the events are saved as "All Day" event, regardless the user selected time slot.
Calendar | It should be possbile to edit or delete any event.
Calendar | Event; Location: Drop drop menu should be available as soon as user start to type locations.
Calendar | Previous dates should be highlight or shadow.
Calendar | How to add calender notes?
Calendar | How to set attendees rights (e.g modify or delete, view)
Video | As soon as someone reject the call the video panel display some message (i.e. Redial, Dimiss or etc.)
Video | Leave Call Alert should not be there if already move on to another call.
Calendar | User should have option to select unique color for their events, so it can be differentiate between share events.
File Sync | Tool tips should be available on mouse hover for all options.
File Sync | Star options should rapidly work on mouse clicks.
File Sync | How to set rights (e.g. Editor, Commenter, Viewer) if user sharing the folder or file with specific people???
File Sync | File size restrictions should be apply on file/folder uploading, as currently users can even upload windows image file and stuck on loader.
Notes | Just adjacent to "+" sign cursor is blinking with default text Add New Note, however its not possible to add new note from there.
Notes | How to delete notes ??
General | How to mark all notification as read at once ??
File Sync | Folders are not created whenever user add special character in folder name.
Markets | Currencies are not available for any tenure.
Markets | Indices values should be available all the time. Just try to navigate markest's different tabs and tenure, adn then notice the indices are not reflecting. or may need to optimize.
Insights | Pane values and dates are not updating.
Talk | Other languages fonts are not supported basically question marks are text in other language

## Faisal sb (hidden)
S. No. |  | Observation/Description/ Steps to reproduce | Category | Developer | Status | Remarks | Area | Resource | Status
| Talk App | Can’t see who all are in this group. On app (Iphone) |  |  |  |  | Access Management | Arsalan | Open
| Talk App | Sending thumbs up converts to 2 ? Emoticon not supporting in App (Iphone) |  |  |  |  | Address Book | Danish | Resolved
| Talk | Need to change emoticons |  |  |  |  | Authorization | Fahad | Tested
| Talk | Is there any way I can see info on any individual group message |  |  |  |  | Calendar | Hamza | Acknowledged
| Talk | I continued my previous session from yesterday to today. Markets tab is not updated (Mac) |  |  |  |  | Daily Digest | Ovais | Re-Open
| Talk | Other point: Clicking anywhere hides the Talk panel. Talk panel should be available at all times unless manually hidden. Even if I use another button in side panel (e.g. apps or plugins, etc |  |  |  |  | Email |  | Ignore
| Talk App | Click on pdf file a alert message appeared. Ref: Axis testing group date 12 Aug (Iphone) |  |  |  |  | Feeds |  | Discussion
| Talk App | Why Image starting to load all the time when clcik on chat (Iphone) |  |  |  |  | File Sync
| Talk App | Couldn’t forward image to 3rd party (Iphone) |  |  |  |  | Greeting Screen
|  | 2021-12-15 |  |  |  |  | Markets
| Talk | Axis testing group missing in recent chat |  |  |  |  | Media
| Talk App | User not sign in message appear in app, when login |  |  |  |  | News Ticker
| Talk App | When click on notification first time when open app, app becomes crash |  |  |  |  | Notes
Notifications
Settings
Talk
User Profile
User Status
Video
Deposit Sheet
Rate Sheet
General
Internal News

## Waqas (hidden)
S. No. | Area | Observation/Description/ Steps to reproduce | Category | Developer | Status | Remarks | Area | Resource | Status
| Email | Email chain should develop |  |  |  |  | Access Management | Arsalan | Open
| File Sync | Collabora not working |  |  |  |  | Address Book | Danish | Resolved
| Calendar | While creating event hour selection option should not be dependent on AM, PM |  |  |  |  | Authorization | Fahad | Tested
| Calendar | While creating event hour selection option should not be dependent on AM, PM |  |  |  |  | Calendar | Hamza | Acknowledged
| Calendar | While creating event video link option should be available |  |  |  |  | Daily Digest | Ovais | Re-Open
| Calendar | When add attendee email to attendee not generating |  |  |  |  | Email |  | Ignore
| Calendar | When edit in event notification should generate |  |  |  |  | Feeds |  | Discussion
| Talk | Sometime doubling of Talk message |  |  |  |  | File Sync
| Talk | Notification not stable, group notification |  |  |  |  | Greeting Screen
| Talk | Overall font formatting should be same |  |  |  |  | Insights
|  | 2021-12-15 |  |  |  |  | Markets
| Email | Replying to all - when replying to all, my email address is not being reoved from the mailing list |  |  |  |  | Media
| Email | My sent emails are shown in " Drafts" |  |  |  |  | News Ticker
| Email | If I am marking any email with "star", it is not showing on my mailbox |  |  |  |  | Notes
| Email | axis email not synced with original gmail. suggest we work on this. |  |  |  |  | Notifications
Settings
| Email | Email search option should be available |  |  |  |  | Talk
User Profile
User Status
Video
Deposit Sheet
Rate Sheet
General
Internal News

## Amna (hidden)
S. No. | Area | Observation/Description/ Steps to reproduce | Category | Developer | Status | Remarks | Area | Resource | Status
|  | 2021-12-28 |  |  |  |  | Access Management | Arsalan | Open
[7 empty] | Address Book | Danish | Resolved
[7 empty] | Authorization | Fahad | Tested
[7 empty] | Calendar | Hamza | Acknowledged
[7 empty] | Daily Digest | Ovais | Re-Open
[7 empty] | Email |  | Ignore
[7 empty] | Feeds |  | Discussion
File Sync
Greeting Screen
Insights
Markets
Media
News Ticker
Notes
Notifications
Settings
Talk
User Profile
User Status
Video
Deposit Sheet
Rate Sheet
General
Internal News

## Shumaila (hidden)
S. No. | Area | Observation/Description/ Steps to reproduce | Category | Developer | Status | Remarks | Area | Resource | Status
| General | page is not loading |  |  |  |  | Access Management | Arsalan | Open
| General | only icons are visible, unable to click them |  |  |  |  | Address Book | Danish | Resolved
| General | Fetching/ configuring email took time |  |  |  |  | Authorization | Fahad | Tested
| Email | attachments take very long time & while attaching files suddenly page went blank (just the email container) |  |  |  |  | Calendar | Hamza | Acknowledged
| Email | not showing any emails in sent, draft & unread (just showing inbox mails) |  |  |  |  | Daily Digest | Ovais | Re-Open
| General | overlapping of bell icon & news time track |  |  |  |  | Email |  | Ignore
| Email | unable to send simple test email as well (without any attachment) - it went blank |  |  |  |  | Feeds |  | Discussion
File Sync
|  | 2021-12-15 |  |  |  |  | Greeting Screen
| Feeds | auto logout account while clicking on admin panel, If admin right not given admin Panel shouldn't be displayed to user |  |  |  |  | Insights
| Minisite | minisite not configured appears when change department |  |  |  |  | Markets
| File Sync | unable to upload file in a particular folder |  |  |  |  | Media
| Email | taking time to download image file |  |  |  |  | News Ticker
Notes
2022-01-16
| Talk App | Getting crash after every 5 to 10 mints/ Tresmark crashed |  |  |  |  | Notifications
| Talk App | Loading time is too long/ slow |  |  |  |  | Settings
| Talk | Unable to login at the same time (web & mobile) |  |  |  |  | Talk
User Profile
User Status
Video
Deposit Sheet
Rate Sheet
General
Internal News

## Komal (hidden)
S. No. | Area | Observation/Description/ Steps to reproduce | Category | Developer | Status | Remarks | Area | Resource | Status
|  | 2021-12-28 |  |  |  |  | Access Management | Arsalan | Open
[7 empty] | Address Book | Danish | Resolved
[7 empty] | Authorization | Fahad | Tested
[7 empty] | Calendar | Hamza | Acknowledged
[7 empty] | Daily Digest | Ovais | Re-Open
[7 empty] | Email |  | Ignore
[7 empty] | Feeds |  | Discussion
File Sync
Greeting Screen
Insights
Markets
Media
News Ticker
Notes
Notifications
Settings
Talk
User Profile
User Status
Video
Deposit Sheet
Rate Sheet
General
Internal News

## Tech Team (hidden)
Name | Area | Observation/Description/ Steps to reproduce | Category | Developer | Status | Remarks | Area | Resource | Status
|  | 2021-12-28 |  |  |  |  | Access Management | Arsalan | Open
[7 empty] | Address Book | Hamza | Resolved
[7 empty] | Authorization | Omair | Tested
[7 empty] | Calendar | Shayan | Acknowledged
[7 empty] | Daily Digest | Faizan | Re-Open
[7 empty] | Email | Ovais | Ignore
[7 empty] | Feeds | Fahad | Discussion
[7 empty] | File Sync | Sumair
Greeting Screen
Insights
Markets
Media
News Ticker
Notes
Notifications
Settings
Talk
User Profile
User Status
Video
Deposit Sheet
Rate Sheet
General
Internal News

## Kazim (hidden)
Tester | Area | Observation/Description/ Steps to reproduce | Category | Developer | Status | Remarks | Area | Resource | Status
| Email | When Configure email system donot allow to use Axis other widgets untill all email get synced |  |  |  |  | Access Management | Arsalan | Open
| Email | System should pick email ID without pressing enter |  |  |  |  | Address Book | Danish | Resolved
| Email | When undo trash email, Email appear at the bottom of the Inbox |  |  |  |  | Authorization | Fahad | Tested
| Email | Discard option should be replaced with Bin Icon |  |  |  |  | Calendar | Hamza | Acknowledged
| Email | Back button should be available during composing |  |  |  |  | Daily Digest | Ovais | Re-Open
| Video | Response is slow system take time to create call |  |  |  |  | Email |  | Ignore
| Video | During call with user my voice repeating to myself |  |  |  |  | Feeds |  | Discussion
| Video | Share screen not working |  |  |  |  | File Sync
| Video | Chat option not working |  |  |  |  | Greeting Screen
| Video | When click any option user dont intimate that open has been clicked |  |  |  |  | Insights
| Video | When host leave the call, Call should be close to all participant or give an option to assign new host |  |  |  |  | Markets
| Video | After leaving the call system keeping blank space at the bottom of the page |  |  |  |  | Media
| Video | In filter Online user option should be available |  |  |  |  | News Ticker
| Email | In Compose email after adding ID backspace space option not working to remove the ID |  |  |  |  | Notes
| Email | In Compose email there should be a back button option |  |  |  |  | Notifications
| Email | In Compose email, setting option should be removed |  |  |  |  | Settings
| Email | In Compose email, Save and edit option should be in Button format |  |  |  |  | Talk
| Email | Compose email screen should be separate so that user can see backend screen |  |  |  |  | User Profile
| Email | Inbox, Sent, Delete etc option should be displayed in label format or give in mini icons |  |  |  |  | User Status
| Email | In compse email, Email word to be repalced with Compose Email |  |  |  |  | Video
| Email | Alignment issues |  |  |  |  | Deposit Sheet
| Email | Attachement clip size to be small |  |  |  |  | Rate Sheet
| Email | Need to change color for unread emails |  |  |  |  | General
| Email | On hover date. email time should be displayed |  |  |  |  | Internal News
| Email | Need to implement sorting mechanism in email
| Email | On hover sender name all participant in emails should be displayed on hover
| Email | Need to give check box to perform repeated action in single step
| Email | Highlight row when hover and select email emial
| Video | No notification of upcoming call when user on other tab or using different application
| Video | Check option should be available in video contact list
| Video | By default only online users should be visible in the list
| Video | Recent and Missed option shoul be combine
| Video | When ever user hover an icon or text, field should be highlighted
| Video | In kazim system on changing resolution of the screen video screen alignment out
| Video | One user should be active in one call only
| Video | If a user is on another call message should be displayed to caller
| Video | When user is on another call his status should be busy in video list along Already Connected message with disbale video icon
| Video | Video and other panel size should be decreased
| Video | Block user option should be available
| Talk | User should be alerted with tone when receive a new message in talk
| Talk | Tab notification should display user name in tab
| Talk | Share multiple messages to user without creating group
| Talk | If user share link in talk, link not visible to user due blue color background
| Talk | Online and offline contact filter should be available
| Talk | Check option should be available with Talk user to perform repeated task in single step
| Talk | When internet disconnect user status becomes offline, even after internet connect again
| Talk | Multiple file sharing to users
| Talk | Video call option is missing in recent chat
| File Sync | One hover member name should display
| File Sync | Date format to be same in all feature
| File Sync | Recent order issue when change filter
| File Sync | File should open on same screen
| File Sync | After renaming the file or perform any activity container begins to load, This should not happen
| File Sync | Member word relace with Shared user
| File Sync | When open whiteboard NC begins to download zip files
| File Sync | Today activity file should be displayed in different color
| File Sync | Checkbox in file Sync
| Calendar | Create event will be replaced with Calendar icon. when user click on icon calendar open user will click date to create event
| Calendar | Daily, Weekly, Monthly should display on screen as icon
| Calendar | Calendar evnet not reflecting real time
| Calendar | Past event color should be changed
| Calendar | Only upcoming event to be displayed to user
| Calendar | when change filter icon alignment get disturbed
| Calendar | Event duplicate or repeat the same event functionaly should be develop
| Calendar | Popout notification for reminder of upcoming event in calendar should apppear
| Calendar | Video call link should be availble in calendar
2021-12-15

## Compatibility testing
S. No. | Area | Browser | Observation/Description/ Steps to reproduce | Category | Developer | Status | Remarks | Area | Resource | Status | Browser |  | Windows Version | Mac Version
|  |  | Start Date 3rd November | [8 empty] | Safari | Version 5.1.7 (7534.57.2) | Version 14.1 (16611.1.21.161.6)
1 |  | Safari | Login Screen not loading |  | Rafhan | Open |  | Access Management | Arsalan | Open | Safari | Chrome | Version 95.0.4638.69 (Official Build) (64-bit) | Version 95.0.4638.69 (Official Build) (x86_64)
2 |  | Safari | Axis dashobard not loading in safari all screen are blank |  | Rafhan | Open |  | Address Book | Danish | Resolved | Chrome | Firefox | Version 94.0.1 (64 bit) | Version 94.0.2 (64 bit)
3 |  | Safari | Dashboard design is also not accurate |  | Rafhan | Open |  | Authorization | Fahad | Tested | Firefox | Opera | Version:80.0.4170.72 | Version:81.0.4196.60 (x86_64)
4 |  | Opera | News tickers are not sync in chrome and in Opera |  | Rafhan | Open |  | Calendar | Hamza | Acknowledged | Opera | Edge | Version 95.0.1020.44 (Official build) (64-bit) | Version 95.0.1020.44 (Official build) (x86_64)
5 |  | Opera | Brightness level in Opera is dull than other browsers |  | Rafhan | Open |  | Daily Digest | Ovais | Re-Open | Edge | Internet Explorer | Version 21H1 (OS Build 19043.1288)
6 |  | Opera | Opera are fine very close to chrome |  |  |  |  | Email | Rafhan | Ignore
7 |  | Edge | Brightness level in edge is dull than other browsers |  | Rafhan | Open |  | Feeds |  | Discussion
8 |  | Firefox | Login screen opacity is so visible |  |  |  |  | File Sync
9 |  | Firefox | Social media page not loading in firefox |  | Rafhan | Open |  | Greeting Screen
10 |  | Firefox | Reval rates tenors and scroll bar are collapsing with each other |  | Rafhan | Open |  | Insights
11 |  |  | Mac |  |  |  |  | Markets
12 |  | Safari | News Ticker alignment is out |  | Rafhan | Open |  | Media
13 | Insights | Safari | Grid are loading one by one |  |  | Ignore |  | News Ticker
14 | Email | Safari | In compose email when adding email ID upper border is not visible |  | Rafhan | Open |  | Notes
16 | Email | Safari | When click on forward option from menu email fields are blank |  |  |  |  | Settings
17 | Email | Safari | Link icon doubling in safari |  |  |  |  | Talk
| Email | Safari | More than 25 email apearing in the sent box. System not managing 25 emails criteria
18 | Feeds | Safari | In feeds search box cross icon should not be visible |  |  |  |  | User Profile
19 | Feeds | Safari | When change option from dropdown list loader display feeds header at the bottom of the container |  |  |  |  | User Status
20 | Feeds | Safari | Headers are not fixed |  |  |  |  | Video
21 | File Sync | Safari | Menu option is appearing on scroll |  |  |  |  | Deposit Sheet
22 | File Sync | Safari | Moved a file in folder but after uploading new file moved file started to apearing on front |  |  |  |  | Rate Sheet
23 | File Sync | Safari | Scrolling not performing properly by using mouse in all tools |  |  |  |  | General
24 | File Sync | Safari | Burger menu not appearing in medium view |  |  |  |  | Internal News
25 | Calendar | Safari | Date showing invalid date
26 | Calendar | Safari | After creating event modal didn't close
27 | Calendar | Safari | Event didnot appear in real time. Month filter was selected event didn't appear until change the filter
28 | Talk | Safari | Only chat box header appearing irrespective of the tab selection
29 | Video | Safari | Video screen not stable. Scroll is active back and front both
30 | Snap | Safari | Displaying win>shift>S where as should display mac short cut key
33 | Email | Chrome | Link icon is overapping in compose email
34 | File Sync | Chrome | Medium screen not properly adjusted giving scroll vertical and horizontal both
35 | Feeds | Chrome | Creating horizontal scroll in both medium and large screen
36 | Feeds | Chrome | On loading screen headers displaying at the botton that should not appear
37 | Notes | Chrome | On loading screen headers displaying at the botton that should not appear
38 | Talk | Chrome | When Add user in chat in any tab Alignment is out
39 | Talk | Chrome | Unable to add user for new conversation
40 | Snap | Chrome | Displaying win>shift>S where as should display mac short cut key
41 | Insights | Edge | Grid are loading one by one
42 |  | Edge | Almost all above mentioned issues exist in Edge also
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99